## HLR
functionality id | functionality name | Description
1 | check website Url | while entering website Url in addressbar website open properly.
2 | check login button | while clicking on the login button, it is login properly and also open the new page.
3 | check side menu button | while clicking on the menu button, it is working properly and also had opened.
10 | check all items | while clicking on the all items, it is working properly, but sometime it has logged out.
11 | check about | while clicking on the about, it is working properly, but clicking on about another website has opened.
12 | check logout button | while clicking on logout button, it is working properly, and also had logged out.
13 | check reset app state | while clicking on the reset app state, it is working properly.
20 | check close icon | while clicking on the close icon, it is working properly.
21 | check cart icon | while clicking on the cart button, it is working properly and also had opened.
22 | check continue shopping button | while clicking on the continue shopping button, it is working properly, and also had opened.
23 | check checkout button | While clicking on the checkout button, it is working properly, and also had opened.
24 | check continue button | While clicking on the continue button, it is working properly, and also had opened.
25 | check cancel button | while clicking on the cancel button, it is working properly.
26 | same as 22 id | while clicking on the continue shopping button, it is working properly, and also had opened.
27 | check filter dropdown menu | while clicking on the dropdown icon, it is working properly, but when clicking on dropdown arrow, it it not working.
28 | check dropdown options | while clicking on the all dropdown options, it is all working properly.
29 | check product name link | while clicking on the product name link, it is working properly, but sometime it has logged out.
40 | check add to cart button | while clicking on the add to cart button, it is working properly and has also added to cart.
41 | check remove button | whille clicking on the remove button, it is working properly and has also removed from the cart.
42 | check back to product | while clicking on the back to product link, it is working properly, but sometime it has logged out
43 | check image | while clicking on the image, it is working properly and also has opened the page.
44 | same as 40 id | while clicking on the add to cart button, it is working properly and has also added to cart.
45 | same as 41 id | whille clicking on the remove button, it is working properly and has also removed from the cart.
46 | same as 21 id | while clicking on the cart button, it is working properly and also had opened.
47 | same as 41 and 45 id | whille clicking on the remove button, it is working properly and has also removed from the cart.
48 | same as 23 id | While clicking on the checkout button, it is working properly, and also had opened.
49 | same as 24 id | While clicking on the continue button, it is working properly, and also had opened.
50 | same as 25 id | while clicking on the cancel button, it is working properly.
51 | check finish button | while clicking on finish button, it is working properly, and also had opened.
52 | check back to home button | while clicking on back to home button, it is working properly, and also had opened.
53 | check twitter icon | while clicking on twitter icon, it its working properly, and also had opened.
54 | check facebook icon | while clicking on facebook icon, it its working properly, and also had opened.
55 | check linkedin icon | while clicking on linkedin icon, it its working properly, and also had opened.
56 | same as 12 id | while clicking on logout button, it is working properly, and also had logged out.

## TestCase
Test Case ID | Functionality ID | Test Case Name | Precondition | Step | Test Data | Expected Result | Actual Result | Status
1 | 1 | check website Url | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key | N.A | To open the website properly | as per the expected result | pass
2 | 2 | check login button with correct username and password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret_sauce | user dashboard should be properly opened with the user details | as per the expected result it is getting logged in but the user dashboard details are not show properly | Fail
3 | 2 | check login button with blank username and blank password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: | to display the proper message | it is not showing the proper validation message | Fail
4 | 2 | check login button with correct username and blank password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: | to display the proper message | it is not showing the proper validation message | Fail
5 | 2 | check login button with blank username and correct password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: secret_sauce | to display the proper message | it is not showing the proper validation message | Fail
6 | 2 | check login button with username having special characters and correct password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user@@ password: secret_sauce | to display the proper message | it is not showing the proper validation message | Fail
7 | 2 | check login button with correct username and having special characters with password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret_sauce@@ | to display the proper message | it is not showing the proper validation message | Fail
8 | 2 | check login button with username having special characters and password as blank | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user@@ password: | to display the proper message | it is not showing the proper validation message | Fail
9 | 2 | check login button with blank username and having special characters with password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: secret_sauce@@ | to display the proper message | it is not showing the proper validation message | Fail
10 | 2 | check login button with username having digit and correct password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user123 password: secret_sauce | to display the proper message | it is not showing the proper validation message | Fail
11 | 2 | check login button with correct user name and having digit with password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret_sauce123 | to display the proper message | it is not showing the proper validation message | Fail
12 | 2 | check login button with username having white space between them and correct password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard user password: secret_sauce | to display the proper message | it is not showing the proper validation message | Fail
13 | 2 | check login button with correct username and white space between them in password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret sauce | to display the proper message | it is not showing the proper validation message | Fail
14 | 2 | check login button with username having white space between them and password as blank | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard user password: | to display the proper message | it is not showing the proper validation message | Fail
15 | 2 | check login button with username as blank and white space between them in password | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: secret sauce | to display the proper message | it is not showing the proper validation message | Fail
16 | 3 | check side menu button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu | N.A | side menu is getting opened | as per expected result | pass
17 | 4 | check all items | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on all items | N.A | it is not opening | as per expected result | Fail
18 | 11 | check about | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on about | N.A | about button is working properly but while click on about button different website opened | as per expected result | Fail
19 | 12 | check logout button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on logout button | N.A | logout button is working properly and also had logged out. | as per expected result | pass
20 | 13 | check reset app state | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on reset app state | N.A | it is working properly and also had any changes in website it is back to normal | as per expected result | pass
21 | 20 | check close icon | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on close icon | N.A | it is working properly and also had close all side menu | as per expected result | pass
22 | 21 | check cart icon | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon | N.A | it is working properly and also had opened | as per expected result | pass
23 | 22 | check continue shopping button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on continue shopping button | N.A | it is working properly and also had opened | as per expected result | pass
24 | 23 | check checkout button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button | N.A | it is working properly and also had opened | as per expected result | pass
25 | 24 | check continue button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on continue button | N.A | it is working properly and also had opened | as per expected result | pass
26 | 25 | check cancel button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on cancel button | N.A | it is working properly and also had opened | as per expected result | pass
27 | 26 | same as 22 id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on continue shopping button | N.A | it is working properly and also had opened | as per expected result | pass
28 | 27 | check filter dropdown menu | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on dropdown menu | N.A | while clicking on dropdown menu it is working properly but while I click on dropdown arrow it is not working | as per expected result | Fail
29 | 28 | check dropdown options | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on dropdown menu 5) check dropdown options | N.A | while clicking on dropdown options it is working properly | as per expected result | pass
30 | 29 | check product name link | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link | N.A | while clicking on product name link it is working properly buy some time it has logged out. | as per expected result | fail
31 | 40 | check add to cart button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button | N.A | while clicking on add to cart button it is working properly and also had added to cart | as per expected result | pass
32 | 41 | check remove button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button 6) click on remove button | N.A | while clicking on remove button it is working properly and also had remove from cart | as per expected result | pass
33 | 42 | check back to product | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on back to product | N.A | while clicking on back to product it is working properly buy some time it has logged out. | as per expected result | Fail
34 | 43 | check image | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on image | N.A | while clicking on image it is working properly and also has opened. | as per expected result | pass
35 | 44 | same as 31 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button | N.A | while clicking on add to cart button it is working properly and also had added to cart | as per expected result | pass
36 | 45 | same as 32 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button 6) click on remove button | N.A | while clicking on remove button it is working properly and also had remove from cart | as per expected result | pass
37 | 46 | same as 22 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon | N.A | it is working properly and also had opened | as per expected result | pass
38 | 47 | same as 32 and 36 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button 6) click on remove button | N.A | while clicking on remove button it is working properly and also had remove from cart | as per expected result | pass
39 | 48 | same as 24 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button | N.A | it is working properly and also had opened | as per expected result | pass
40 | 49 | same as 25 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on continue button | N.A | it is working properly and also had opened | as pr expeted result | pass
41 | 50 | same as 26 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on cancel button | N.A | it is working properly and also had opened | as per expected result | pass
42 | 51 | check finish button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on cart icon 5) click on checkout button 6) click on continue button 7) click on finish button | N.A | it is working properly and also had opened | as per expected result | pass
43 | 52 | check back to home button | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on cart icon 5) click on checkout button 6) click on continue button 7) click on finish button 8) click on back to home button | N.A | it is working properly and also had opened | as per expected result | pass
44 | 53 | check twitter icon | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | N.A | while clicking on twitter icon it is working properly and also had opened. | as per expected result | pass
45 | 54 | check facebook icon | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | N.A | while clicking on facebook icon it is working properly and also had opened. | as per expected result | pass
46 | 55 | check linkedin icon | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button | N.A | while clicking on linkedin icon it is working properly and also had opened. | as per expected result | pass
47 | 56 | same as 19 test case id | internet and browser must be in the working condition | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on logout button | N.A | logout button is working properly and also had logged out. | as per expected result | pass

## Test Scenario
Test Case ID | Functionality ID | Test Summery | Step | Test Data | Expected Result | Actual Result
1 | 1 | check website Url | 1) www.saucedemo.com 2) press enter key | N.A | To open the website properly | as per the expected result
16 | 3 | check side menu button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu | N.A | side menu is getting opened | as per expected result
19 | 12 | check logout button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on logout button | N.A | logout button is working properly and also had logged out. | as per expected result
20 | 13 | check reset app state | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on reset app state | N.A | it is working properly and also had any changes in website it is back to normal | as per expected result
21 | 20 | check close icon | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on close icon | N.A | it is working properly and also had close all side menu | as per expected result
22 | 21 | check cart icon | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon | N.A | it is working properly and also had opened | as per expected result
23 | 22 | check continue shopping button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on continue shopping button | N.A | it is working properly and also had opened | as per expected result
24 | 23 | check checkout button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button | N.A | it is working properly and also had opened | as per expected result
25 | 24 | check continue button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on continue button | N.A | it is working properly and also had opened | as per expected result
26 | 25 | check cancel button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on cancel button | N.A | it is working properly and also had opened | as per expected result
27 | 26 | same as 22 id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on continue shopping button | N.A | it is working properly and also had opened | as per expected result
29 | 28 | check dropdown options | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on dropdown menu 5) check dropdown options | N.A | while clicking on dropdown options it is working properly | as per expected result
31 | 40 | check add to cart button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button | N.A | while clicking on add to cart button it is working properly and also had added to cart | as per expected result
32 | 41 | check remove button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button 6) click on remove button | N.A | while clicking on remove button it is working properly and also had remove from cart | as per expected result
34 | 43 | check image | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on image | N.A | while clicking on image it is working properly and also has opened. | as per expected result
35 | 44 | same as 31 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button | N.A | while clicking on add to cart button it is working properly and also had added to cart | as per expected result
36 | 45 | same as 32 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button 6) click on remove button | N.A | while clicking on remove button it is working properly and also had remove from cart | as per expected result
37 | 46 | same as 22 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon | N.A | it is working properly and also had opened | as per expected result
38 | 47 | same as 32 and 36 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on add to cart button 6) click on remove button | N.A | while clicking on remove button it is working properly and also had remove from cart | as per expected result
39 | 48 | same as 24 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button | N.A | it is working properly and also had opened | as per expected result
40 | 49 | same as 25 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on continue button | N.A | it is working properly and also had opened | as pr expeted result
41 | 50 | same as 26 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on cart icon 5) click on checkout button 6) click on cancel button | N.A | it is working properly and also had opened | as per expected result
42 | 51 | check finish button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on cart icon 5) click on checkout button 6) click on continue button 7) click on finish button | N.A | it is working properly and also had opened | as per expected result
43 | 52 | check back to home button | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on cart icon 5) click on checkout button 6) click on continue button 7) click on finish button 8) click on back to home button | N.A | it is working properly and also had opened | as per expected result
44 | 53 | check twitter icon | 1) www.saucedemo.com 2) press enter key 3) click on login button | N.A | while clicking on twitter icon it is working properly and also had opened. | as per expected result
45 | 54 | check facebook icon | 1) www.saucedemo.com 2) press enter key 3) click on login button | N.A | while clicking on facebook icon it is working properly and also had opened. | as per expected result
46 | 55 | check linkedin icon | 1) www.saucedemo.com 2) press enter key 3) click on login button | N.A | while clicking on linkedin icon it is working properly and also had opened. | as per expected result
47 | 56 | same as 19 test case id | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on logout button | N.A | logout button is working properly and also had logged out. | as per expected result

## Defect Report
Defect ID | Functionality ID | Test Case Name | Reproduced Step | Test Data | Defect types | Defect Severity | Defect Priority | Expected Result | Actual Result | Teser Name | Attchment | Status
2 | 2 | check login button with correct username and password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret_sauce | Functionality,Usability | Medium | High | user dashboard should be properly opened with the user details | as per the expected result it is getting logged in but the user dashboard details are not show properly | Nirav Goti | https://drive.google.com/file/d/1dZoqL-u3bowtAFMZeBcGFcgOtrA7wVY2/view?usp=share_link | Open
3 | 2 | check login button with blank username and blank password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1Hn4k2hdLQ2g7DmhZPxl2HwWktv-J_eYJ/view?usp=share_link | Open
4 | 2 | check login button with correct username and blank password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/16NZa14XF5OedLdTZgcPe7HWlrysa8bhJ/view?usp=share_link | Open
5 | 2 | check login button with blank username and correct password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: secret_sauce | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1pnxIZ2IdC91hBJjJfc7b2dYE5OSEbatB/view?usp=share_link | Open
6 | 2 | check login button with username having special characters and correct password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user@@ password: secret_sauce | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/11jhmSlO-lDXP81b8x3M_ND2DyAJBVTSr/view?usp=share_link | Open
7 | 2 | check login button with correct username and having special characters with password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret_sauce@@ | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1CWBSzN15ALiuWjldiPSKDLiMc_QAoFx_/view?usp=share_link | Open
8 | 2 | check login button with username having special characters and password as blank | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user@@ password: | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/12O60w7LEWDY572Ys13NJiScFb2RHXhD0/view?usp=share_link | Open
9 | 2 | check login button with blank username and having special characters with password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: secret_sauce@@ | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1swRikMIX_vK6BgjbwFIysrZc6ic1XU48/view?usp=share_link | Open
10 | 2 | check login button with username having digit and correct password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user123 password: secret_sauce | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1Utiaz9EF41_bt7dv3c3h2pbc5JjJ39Ac/view?usp=share_link | Open
11 | 2 | check login button with correct user name and having digit with password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret_sauce123 | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1a3G3YeZES0_nfQ8Qg-NlcTmTpfAGIoCO/view?usp=share_link | Open
12 | 2 | check login button with username having white space between them and correct password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard user password: secret_sauce | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1o6HUj0PqQcvucgp8HQg9MVDNKty747Gh/view?usp=share_link | Open
13 | 2 | check login button with correct username and white space between them in password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard_user password: secret sauce | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1MtKwDvTFIwqD4Ji-exR4YfjnIyjGineg/view?usp=share_link | Open
14 | 2 | check login button with username having white space between them and password as blank | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: standard user password: | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1RTD15u0Rd7VIqK9qpaZMG-lL26p9TcCz/view?usp=share_link | Open
15 | 2 | check login button with username as blank and white space between them in password | 1) www.saucedemo.com 2) press enter key 3) click on login button | user name: password: secret sauce | Functionality,Usability | Medium | Low | to display the proper message | it is not showing the proper validation message | Nirav Goti | https://drive.google.com/file/d/1IEj9YgHj6wI8zfVlfaClmnh0p5Wcui1p/view?usp=share_link | Open
17 | 4 | check all items | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on all items | N.A | Functionality,Usability | Low | Medium | it is not opening | as per expected result | Nirav Goti | https://drive.google.com/file/d/1DbwL26elHVJX2a9gQjG5iZ2WETe121ON/view?usp=share_link | Open
18 | 11 | check about | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on side menu 5) click on about | N.A |  |  |  | about button is working properly but while click on about button different website opened | as per expected result | Nirav Goti |  | Open
28 | 27 | check filter dropdown menu | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on dropdown menu | N.A |  |  |  | while clicking on dropdown menu it is working properly but while I click on dropdown arrow it is not working | as per expected result | Nirav Goti |  | Open
30 | 29 | check product name link | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link | N.A |  |  |  | while clicking on product name link it is working properly buy some time it has logged out. | as per expected result | Nirav Goti |  | Open
33 | 42 | check back to product | 1) www.saucedemo.com 2) press enter key 3) click on login button 4) click on product name link 5) click on back to product | N.A |  |  |  | while clicking on back to product it is working properly buy some time it has logged out. | as per expected result | Nirav Goti |  | Open